Project Proposal Draft 1 Report

Dmart (Mumbai, India) Warehouse Automation

Engineering Project Management (EMGT 5220)

Spring 2025 Term Project

Team 1: Taskmasters

Instructor: Professor Bajracharya, Sharad

Northeastern University

Point of contact: More, Vaibhav

more.vaib@northeastern.edu | (857) 506-7823

Team Members

More Vaibhav

Naresh Hemanth

Prasannakumar Yashaswi

Raval Harsh

Taheri Rojin

Tanpure Saloni

Vijayakumar Niroopa

Table of Contents

1.0 INTRODUCTION	1

2.0 PURPOSE AND OBJECTIVES	2

2.1 Purpose	2

2.2 Objective	2

3.0 IMPLEMENTATION PLAN	3

3.1 Work Breakdown Structure	3

Project Initiation:	3

Planning:	3

Procurement:	3

Execution:	4

Testing and Optimization:	4

Deployment:	4

Post-Launch Maintenance and Support:	4

4.0 TEAM CREDENTIALS	6

APPENDICES	8

REFERENCES	11

# INTRODUCTION

D-Mart is one of the most valued retail chains across India, renowned for selling groceries and essentials on an "EveryDay Low Price" basis to people across the country. As the retail landscape evolves efficiency in warehousing and supply chain operations has become a critical factor in maintaining competitive edge. However, D-Mart's current warehouse management system heavily relies on the manual labor leading to inefficiencies such like the slow order fulfillment, high operational costs and the frequent inventory discrepancies. These challenges not only hinder the company's ability to meet growing consumer demands but also leads to restrict its potential for scalable expansion in a fast-paced market.

The proposed project aims at remodelling operations in Dmart warehouses from conventional manual processes to a robotic driven one with much higher efficiencies, accuracy, and scalability. By integrating the advanced robotic solutions, the warehouse will be transformed into highly efficient, technologically integrated ecosystem. The integration of these cutting-edge technologies with D-Mart’s existing Warehouse Management System (WMS) will further enhance real time inventory tracking, predictive restocking and data driven decision making, ultimately improving operational agility. The solution will thereby help in efficient handling of goods, space utilization optimization and smoothening of workflow.

This robotic automation has helped many retail giants like Amazon and Walmart reduce their processing time and improve inventory accuracy to set the industry standard [1] [2]. Similar measures adopted by DMart can thus be expected to bring down the processing time by up to about 40%, increase productivity by 35% and reduce labour cost by 30 to 40% [3]. This will help and contribute towards a more reliable and scalable supply chain hence also ensuring faster replenishment cycles and greater customer satisfaction.

This transition will not only streamline warehouse operations but also strengthen D-Mart’s supply chain resilience, enabling faster replenishment cycles, improved inventory control, and enhanced customer satisfaction. By embracing automation, D-Mart can position itself at the forefront of retail innovation ensuring long term operational efficiency while continuing to deliver value driven service to its customers.

# 2.0 PURPOSE AND OBJECTIVES

## 2.1 Purpose

DMart has an existing warehousing system with inventory replenishment which is slow and prone to human error, due to manual processes. Contributing to operating expenses, this causes longer replenishment cycles and reduced product stock availability while promoting customer dissatisfaction.

The project addresses these issues with robotics driven automated warehousing using Automated Storage and Retrieval Systems AS/RS and Autonomous Mobile Robots AMRs. The AS/RS will optimize maximum vertical storage and space optimization. AMRs will automate the movement of goods to speed up the sorting, picking, and dispatching of goods [4]. By comparing the performance benchmarks of various companies, we expect to increase our order accuracy to 99.7%, the order fulfilment time by 30%, and lower fulfillment costs by 25% [3][7]. This will scale and enable supply chains to become faster and more reliable. Ultimately, improves operation excellence and customer satisfaction.

## 2.2 Objective

- The objective of this project is to automate warehouse operations, minimize the human intervention using robots for material handling. Automated Storage and Retrieval Systems (AS/RS) will be deployed to optimize space utilization, enabling better vertical storage and maximizing warehouse capacity. Autonomous Mobile Robots (AMRs) will be used to the direct material flow without any of the human intervention it will also facilitate the real time material movement tracking and also help to ensure a smoother and faster workflow.

- The project will also aim to improve the inventory accuracy and reduce labour costs. The repetitive tasks will be automated which will lead to lower operational expenses along with allowing the workforce to focus on more strategic functions to help productivity.

- Order fulfilment will be streamlined by using picking, moving, and dispatching processes. This will also lead and help to reducing order processing times and optimizing replenishment cycles also. Overall automation will helps us to lead to faster deliveries and will also improve customer satisfaction. These enhancements shall collectively contribute to scalable, agile and a industry leading warehouse management system.

# 3.0 IMPLEMENTATION PLAN

## 3.1 Work Breakdown Structure

The project will be implemented in seven phases. The phases facilitate systematic implementation of the warehouse automation system.

### Project Initiation:

In the initial stage the project sponsor and the key stakeholders will define the project’s purpose, goals and the high-level scope. To evaluate technical, financial and operational aspects a thorough feasibility study will be carried out and key stakeholders will be identified, and their roles and responsibilities will also be clarified. To guide the decision-making processes a preliminary schedule and budget outline are also established. To ensure alignment with the business objectives the critical success factors and major risks will be documented. Formal project charter sign off will be obtained signifying agreement from the senior management. Resources will be tentatively allocated, and the team structure will be proposed and laying the foundation for detailed planning and eventual smooth execution.

### Planning:

In the planning stage the project requirements will be gathered and then refined into comprehensive specifications. To identify the deliverables and subdivide the tasks into manageable units the Work Breakdown Structure will be developed. To incorporate dependencies, milestones and the resource allocation a detailed project schedule will be created. The budget will be finalized which will reflect the labor costs, materials and contingencies. The risk management strategies will be formulated where highlighting potential issues and the mitigation plans. To ensure transparent reporting and stakeholder engagement communication protocols will be established. Quality standards will be defined aligning deliverables with the organization benchmarks. After the formal approval of the project management plan is secured which will be enabling a controlled transition to execution activities and oversight.

### Procurement:

To fulfill the project requirements in the procurement phase necessary resources, tools and services will be identified and sourced. The vendor evaluation criteria are defined with emphasis on cost, quality and delivery deadlines. The request for proposals will be distributed and the supplier bids will be compared for the best value. After that the contract negotiations will also ensure favorable terms and  risk allocation and compliance with the legal standards. Then the purchase orders are issued and delivery schedules will be established to coordinate with the logistics. The procurement team will collaborate with stakeholders to validate the product specifications, make invoices and manage any changes that come after that. At last, the supplier performance will be tracked through audits which will ensure the adherence to the contractual obligations and alignment with the project objectives.

### Execution:

In the execution phase the project team will implement the planned tasks to produce the deliverables. The detailed technical designs are also translated into practical solutions and development work is undertaken according to the established standards only. Then the project managers manage resources, monitor progress and also resolve bottlenecks to maintain the schedule integrity. The regular status meetings and communication updates will keep the stakeholders informed of achievements and whatever challenges come in the project. Quality control measures will be applied throughout the project which will ensure deliverables comply with specifications and performance expectations. After each final works and submissions, the issues are documented and addressed properly and there will be collaboration among cross functional teams for that. The project team will have continuous oversight of scope, budget and timeline to keep the project on track and setting the stage for subsequent testing.

### Testing and Optimization:

In this phase the comprehensive testing will validate the system functionality, performance and reliability. The test cases will be derived from the project requirements and will use scenarios covering the unit integration system and the user acceptance testing. The quality assurance team will also simulate the real-world conditions to identify the defects, confirm data accuracy and assess responsiveness under peak loads also. All issues that are encountered will be logged, prioritized and resolved in the iterative cycles ensuring continuous improvement after that. The performance optimization will be applied to refine the system architecture, enhance speed and reduce the resource usage. At the end of this phase the regression tests will confirm the stability after changes in system where user feedback will help fine tune the features. This phase will ensure a robust and efficient solution with reliability and ready for deployment activities.

### Deployment:

During deployment the finalized solution is then transitioned from the testing environment into the production setting with respect to operations of a functioning warehouse. Detailed deployment plans outline each step including data migration, system configuration and the user orientation. Change management processes guide and helps the people involved in project for good communication, ensuring stakeholders are aware of updates, timelines are meet, and the potential impacts in the project. If required phased rollouts and the pilot testing are performed too to mitigate any sort of the disruption. Technical support teams stand by to the address unforeseen issues and the streamline adoption. Training materials, documentation and knowledge transfer sessions empowers and helps end users to utilize new features effectively. Sign offs validate successful deployment confirming that the system meets predefined acceptance criteria, production readiness and is fully operational as per the needs and requirement.

### Post-Launch Maintenance and Support:

In the post-launch phase, the project transitions from ongoing maintenance and support to ensuring sustained functionality for user satisfaction. A dedicated support framework is used to address the inquiries of users, in resolving technical glitches and to manage the software updates. Performance monitoring tools can be used to track the system health and to generate insights for timely optimization. These planned enhancements or new features can then be evaluated against evolving business needs and to maintain the alignment with strategic goals. Regular backups, security patches, and infrastructure checks can help safeguard our data integrity and compliance. Feedback loops can also allow the users to suggest improvements while analytics guide iterative adjustments for peak efficiency. This continuous support model preserves system reliability, fosters adoption, and extends project value.

# 4.0 TEAM CREDENTIALS

More, Vaibhav is a graduate student who is pursuing a Master of Science in Engineering Management. With a focus on the construction management and project execution. He previously worked in the construction industry as a Project Engineer gaining experience in planning, procurement and stakeholder coordination across Industrial, commercial and residential projects. His expertise in budget management, scheduling and construction compliance ensures seamless integration of civil, mechanical and electrical components in Dmart warehouse automation project. His experience in MS Project for the scheduling and resource optimization combined with his background in engineering management enables and helps him to contribute effectively to the projects requiring a balance of technical expertise and managerial acumen.

Naresh, Hemanth is a graduate student pursuing a Master of Science in Engineering Management and is currently working on supply chain engineering and project management. He has previous experience at EBTS as a Supply Chain Intern where he has worked on demand forecasting and inventory optimization for the company. He has a strong background in computer science with the expertise in Python and data analytics which has enabled him to develop many innovative solutions for automation and optimization of process. His technical acumen combined with his project management skills enables him to contribute effectively to projects.

Prasannakumar, Yashaswi is pursuing Master of Science in Engineering Management with special interest in supply chain management and optimization. His mathematics and technical background with engineering and problem-solving career stand him in good stead. His leadership potentially demonstrated by the effort that has gone into developing a Math Club at PES University and organizing gigantic scale events like Bharat Unleashed, Samarpana and others, surely speaks of his capability to manage team effort and innovation. With PES University and TeaminUp Private Ltd. industrial experience, Yashaswi is aware of data-driven decision making, process improvement, and system improvement. His attempt to implement linear programming and mathematical modeling in solving actual supply chain-based problems and searching for information to share relentlessly on LinkedIn blogs are those which indicate a tilt towards the topic and its dissemination in the post-solutionist thinking era.

Raval Harsh is a mechanical engineering and is doing his master degree in engineering management now. He has more than 5 years of experience in the manufacturing, design and working of large projects. He also has knowledge in the process improvement and technical problem solving related to mechanical system design and that will also be his contribution to the project. His skills related to the operational analysis will also help the efficient design of the mechanical systems of the project.

Taheri, Rojin is currently pursuing her master’s in engineering management and has a Bachelor of Industrial Engineering, currently focusing on Project Management. She gained her experience as project manager intern and then project coordinator in a Water Bottle Manufacturing. Her proficiency in Power BI and Tableau allows her to identify trends and enhance efficiency. With expertise in agile scheduling and developing work breakdown structures (WBS) in MS Project, she plays a key role in ensuring projects stay on track and are completed on time.

Tanpure Saloni is a Bachelor’s in Electronics and Telecommunications and currently is pursuing Masters in Engineering Management. She has formerly worked as a research and development Intern and product management intern in India. These internships helped her gain deep knowledge about technology, management, resource procurement which prove to be very critical in business operations. Her work in testing and process optimisation aligned with creating an automated warehouse system.

Vijayakumar, Niroopa is currently a graduate student pursuing Master of Science in Engineering Management and has a bachelor’s degree in civil engineering, currently focusing on Project Management. She gained her expertise in Customer Relationship Management while working for Zoho and Skyways Technologies as a Technical Support Engineer (Zoho CRM) and Intern Project Trainee. Her skills, international experience and strong communication skills will give valuable insights and contribute to the team.

# APPENDICES

Appendix A: Work Breakdown Structure

WBS for Dmart Warehouse Automation. 1.0 Project Initiation Phase. # 1.1 Project Kick-Off & Team Formation. # 1.1.1 Identify and assemble project team members. # 1.1.2 Define project scope, objectives, and deliverables. # 1.1.3 Develop a communication plan with stakeholder contact details. # 1.2 Stakeholder Engagement & Approvals. # 1.2.1 Identify internal and external stakeholders (Dmart, vendors, regulators). # 1.2.2 Conduct initial stakeholder meetings and finalize requirements. # 1.2.3 Obtain necessary approvals and permits. # 1.3 Project Charter & Documentation. # 1.3.1 Draft project charter and define key performance indicators (KPIs). # 1.3.2 Review and obtain necessary approvals. 2.0 Planning Phase. # 2.1 Initial Feasibility Study. # 2.1.1 Conduct architectural, structural and site assessment. # 2.1.1.1 Floor plan architectural planning and development. # 2.1.1.2 Grade slab and shear wall NDT testing, followed by soil testing. # 2.1.2 Preliminary material flow analysis. # 2.1.3 Initial mechanical parameters requirements estimate based on analysis results. # 2.1.4 Estimating increase in electrical load. # 2.1.5 Prepare feasibility reports and obtain approvals. # 2.2 Risk Assessment & Compliance. # 2.2.1 Ensure compliance with safety and warehouse automation regulations. # 2.2.2 Identify potential risks and mitigation strategies. # 2.3 System Design & Engineering. # 2.3.1 Civil Engineering. # 2.3.1.1 Structural design for upgrading existing core and shell. # 2.3.1.2 Foundation reinforcement for storage racks and automation machinery. # 2.3.1.3 Fabrication design for framework. # 2.3.1.4 Selection of surface treatment methodologies. # 2.3.1.5 Infrastructure design for power supply. # 2.3.1.6 Civil design for control room, maintenance room, parking & charging station. # 2.3.1.7 Civil infrastructure and layout planning for backup power area (DG Sets). # 2.3.2 Mechanical Engineering. # 2.3.2.1 Detailed warehouse inventory handling analysis. # 2.3.2.2 Calculate automation system parameters based on Inventory Analysis inputs. # 2.3.2.3 Automation Layout and robot pathway planning. # 2.3.2.4 Finalize automation system modelling. # 2.3.2.5 Initial design of an interactive scaled 3D CAD model of the system. # 2.3.2.6 Provide input to the software for the mechanical requirements. # 2.3.3 Electrical Engineering. # 2.3.3.1 Design electrical layout for control & Maintenance room, parking & charging station. # 2.3.3.2 Identify and estimate revised electrical load requirement. # 2.3.3.3 Earthing works planning and layout. # 2.4 Procurement Planning. # 2.4.1 Vendor Identification and prequalification. # 2.4.2 Material and equipment specification finalization. # 2.4.3 Contract drafting and supplier agreements. # 2.4.4 Logistics and supply chain planning. # 2.5 Workforce and resource planning. # 2.5.1 Identify the roles and responsibilities needed for the project. # 2.5.2 Determine the number of personnel needed for each role. # 2.5.3 Estimate the hours required for each role. # 2.5.4 Allocate budget for workforce. 3.0 Procurement Phase. # 3.1 Sourcing construction material (reinforcement, structural steel, concrete raw material). # 3.2 Sourcing surface treatment material and insulation material. # 3.3 Procurement of racks, conveyor systems, AMR and AS/RS. # 3.4 Procurement of transformer, switchgear, DG set and backup fuel. # 3.5 Prourement of battery packs. 4.0 Execution Phase. # 4.1 Civil Work Implementation. # 4.1.1 Dismantle redundant structure and debris removal. # 4.1.2 Extend roofing and sidewalls for additional storage height. # 4.1.3 Conduct soil compaction and ground levelling. # 4.1.4 Marking of foundation and structural reinforcements. # 4.1.5 Concrete Pouring and completion of floor finish and levelling. # 4.1.6 Construction of control room, maintenance room, parking & charging station. # 4.2 Mechanical Implementation. # 4.2.1 On-site installation and assembly. # 4.2.2 Mechanical system integration with robot vendor program and instrumentation sensors. # 4.2.3 Calibration and functional testing. # 4.2.4 Perform initial safety and functionality tests. # 4.2.5 Commissioning. # 4.2.6 Performance validation and trial run. # 4.2.7 Incoporating feedback of trial run to achieve desired level of output. # 4.3 Electrical Implementation. # 4.3.1 Installation of transformer, switchgear, DG sets, electrical panels. # 4.3.2 Laying of earthing and execution of necessary electrical safety protocols. # 4.3.3 Laying of power cables for charging & parking station, control and maintenance room. 5.0 Testing & Optimization Phase. # 5.1 Functional & System Testing. # 5.1.1 Conduct warehouse wide AS/RS and AMR performance tests. # 5.2 Pilot Testing & KPI Tracking. # 5.2.1 Conduct a limited pilot run for order fulfillment. # 5.2.2 Analyze KPIs and collect performance data. # 5.3 Workflow Optimization. # 5.3.1 Optimize automation paths for efficiency. # 5.3.2 Adjust scheduling and warehouse flow based on test results. # 5.4 End-User Training & Feedback. # 5.4.1 Conduct training sessions for warehouse staff. # 5.4.2 Gather user feedback and refine system operations. 6.0 Deployment Phase. # 6.1 Full-Scale Rollout. # 6.1.1 Integration with warehouse management system (WMS). # 6.1.2 Deploy automation system across all warehouse zones. # 6.1.3 Ensure smooth transition and troubleshoot installation issues. # 6.2 Staff Training & Change Management. # 6.2.1 Conduct hands-on training for warehouse employees. # 6.2.2 Implement a change management strategy for staff adaptation. # 6.3 Awareness & Performance Monitoring. # 6.3.1 Launch an awareness campaign for process improvements and safety guidelines. # 6.3.2 Monitor system performance post-deployment. 7.0 Post-Launch Maintenance & Support. # 7.1 System Performance Monitoring. # 7.1.1 Track efficiency and operational throughput. # 7.1.2 Address system anomalies. # 7.2 Scheduled Maintenance & Vendor Coordination. # 7.2.1 Establish a maintenance calendar for AS/RS and AMR systems. # 7.2.2 Coordinate with vendors for periodic servicing and upgrades. # 7.3 Technical Support & Future Scalability Planning. # 7.3.1 Set up a help desk and technical support team. # 7.3.2 Plan future automation scalability based on demand growth.

# REFERENCES

- About Amazon. (2023, April 18). How Amazon deploys robots in its operations facilities. https://www.aboutamazon.com/news/operations/how-amazon-deploys-robots-in-its-operations-facilities

- Digital Commerce 360. (2023, April 5). Walmart turns to warehouse robots - suggests a boost in profit is possible.

https://www.digitalcommerce360.com/2023/04/05/walmart-turns-to-warehouse-robots-suggests-a-boost-in-profit-is-possible/

- Meteor space (2024). Important Warehouse Automation Statistics You Can’t Ignore.

https://www.meteorspace.com/important-warehouse-automation-statistics/

- Jinxiang gu et al. (2007). Research on warehouse operation: A comprehensive review. Elsevier 177(1), 1-21.

https://doi.org/10.1016/j.ejor.2006.02.025

- Supply Chain Digital. (2023, September 15). Amazon's bid to revolutionize warehouse automation.

https://supplychaindigital.com/digital-supply-chain/amazon-warehouse-automation-ai-revolution

- PYMNTS. (2023, July 28). Walmart expects fully automated warehouse to double its capacity. https://www.pymnts.com/walmart/2023/walmart-expects-fully-automated-warehouse-double-its-capacity/

- Techspot. (2025). Amazon's robot-driven warehouses could cut fulfillment costs. https://www.techspot.com/news/106635-amazon-robot-driven-warehouses-could-cut-fulfillment-costs.html